## Intro
IEO RATINGS DATABASE
About this database
The NDB Independent Evaluation Office (IEO) conducts evaluations of NDB-financed projects and programmes. In doing so, it uses internationally recognized evaluation criteria in its evaluations, such as relevance, effectiveness, efficiency, impact, sustainability and others. In assessing project performance, a rating (i.e. score) on a six-point scale (with 6 being the highest score) is assigned to each criterion. (See tab "Evaluation criteria" for explanation of the rating system). This database contains the ratings of every project evaluation completed by IEO since its foundation in April 2022. The database will be updated in real-time as further evaluations are completed. The database is intended as a resource for anyone who wishes to see the results of NDB-financed projects as evaluated by IEO, and for them to conduct their own analytics, as needed. The public sharing of the database through these webpages is a reflection of IEO’s commitment to promoting accountability, transparency and learning. For clarifications or further information, contact Julian Escobar - escobar.julian@x.ndb.int.
To see the full evaluation reports, please refer to the IEO wepages on the NDB website:
https://www.ndb.int/governance/independent-evaluation/completed-evaluations/
MENU
Click on the links below to go to the following tabs:
All project ratings
Evaluation criteria
Glossary

## Project ratings
Ratings Database: Evaluations of NDB-Financed Projects | [22 empty] | Evaluation Criteria
Country | Project Name | Loan ID | Project Area | Sector | Type of Evaluation | Year of Evaluation | Borrower | Sovereignty | Approval Date | Signing Date | Effective Date | Original Closing Date | Actual Closing Date | Total Project Cost (million USD) | Actual Project Cost at Close (USD Million) | NDB Loan Amount Approved (million USD) | Actual NDB Amount at Close (USD Million) | % Disbursement at Completion | Disbursements made | Co-Financing Amount | Co-Financing Institution | Implementing Agency | Relevance | Effectiveness | Efficiency | Impact | Sustainability | NDB's Performance | Borrower Performance | Overall Project Achievement
India | Madhya Pradesh Major District Roads Project | 16IN02 | Madhya Pradesh State | Transport Infrastructure | PPE | 2022 | Republic of India | Sovereign | 2016-11-22 | 2017-03-30 | 2017-06-12 | 2021-03-31 | 2022-03-31 | 463.55 | 463.55 | 350 | 327.74 | 94% | 68 | USD 150 Million | Government of Madhya Pradesh | MP Road Development Corporation Ltd. | 5 | 5 | 4 | 5 | 5 | 3 | 5 | 5
China | Lingang Distributed Solar Power Project | 16CN01 | Shanghai Lingang Industrial Area | Clean Energy and Energy Efficiency | PCRV | 2024 | The People’s Republic of China | Sovereign | 2016-04-13 | 2016-12-21 | 2017-06-06 | 2019-12-21 | 2020-12-21 | 50.165 | N/A | 33.63 | 30.82 | 92% | 22 | RMB 105.9 | Lingang Group | Shanghai Lingang Hongbo New Energy Development Co. Ltd. | 5 | 5 | 4 | 5 | 5 | 4 | 5 | 5
Brazil | Renewable Energy Projects and Associated Transmission | 16BR01 | Bahia, Minas Gerais, Pernambuco, Piauí States | Clean and Renewable Energy Efficiency | PPE | 2023 | The Brazilian Development Bank | Non-Sovereign | 2016-04-13 | 2017-04-26 | 2018-02-09 | 2020-04-26 | 2020-04-26 | 1145 | N/A | 300 | 300 | 100% | 4 | USD 845 Million | Brazilian Development Bank | BNDES (The Brazilian Development Bank) | 4 | 5 | 4 | 5 | 5 | 4 | 5 | 5
China | Luoyang Metro Project | 18CN02 | Henan Province | Transport Infrastructure | PPE | 2023 | The People’s Republic of China | Sovereign | 2018-07-20 | 2018-08-16 | 2018-10-15 | 2022-08-15 | 2021-12-31 | 2775.7 | N/A | 300 | 300 | 100% | 11 | USD 1,311 Million USD 1,164 Million | Commercial Banks People's Government of Luoyang | Luoyang Rail Transportation Co. Ltd. | 5 | 5 | 6 | 6 | 5 | 4 | 6 | 5
South Africa | Greenhouse Gas Emissions Reduction and Energy Sector Development Project | 18ZA02 | North-west, Northern Cape, Mpumalanga, Western Cape Provinces | Clean and Renewable Energy Efficiency | PPE | 2023 | The Development Bank of Southern Africa (DBSA) | Non-Sovereign | 2018-07-20 | 2019-03-15 | 2019-03-15 | 2022-03-14 | 2024-01-29 | 2500 | N/A | 300 | 300 | 100% | 4 | USD 2.2 Billion | DBSA, Commercial Banks and other sources | DBSA (Development Bank of Southern Africa) | 4 | 5 | 4 | 5 | 5 | 4 | 5 | 5
South Africa | Renewable Energy Sector Development Project | 19ZA03 | Northern Cape Province | Clean and Renewable Energy Efficiency | PPE | 2024 | Industrial Development Corporation of South Africa Limited | Non-Sovereign | 2019-03-31 | 2020-02-06 | 2020-02-06 | 2023-12-06 | 2023-12-06 | 1983.5 |  | 82 | 82 | 100% | 5 | USD 1 902 Million | Other Sources | IDC (Industrial Development Corporation of South Africa Limited) | 5 | 5 | 4 | 5 | 5 | 3 | 4 | 5
China | Putian Pinghai Bay Offshore Wind Power Project | 16CN02 | Fujian province | Clean Energy and Energy Efficiency | PPE | 2024 | The People’s Republic of China | Sovereign | 22/11/2016 | 2017-03-09 | 14/11/2017 | 2019-12-31 | 2021-12-21 | 731.56 |  | 294.99 | 289 | 98% | 43 | RMB 0.98 billion RMB 1.68 billion | Domestic banks and other borrowings Equity contribution | Fujian Investment and Development Group Co., Ltd (FIDG) | 5 | 6 | 5 | 6 | 5 | 5 | 5 | 5
Brazil | Para - Sustainable Municipalities Project (Ongoing) | 18BR01 | State of Pará | Urban Development | PPE | 2024 | Federal State of Para | Sovereign | 2018-03-05 | 2019-03-11 | 2019-03-11 | 2024-03-10 | 2024-09-10 | 125 |  | 50 | 50 | 100% | 13 | USD 50 Million USD 25 Million | CAF Government state of Para | Federal State of Para | 5 | 5 | 4 | N/A | N/A | 5 | 5 | 5
India | Bihar Rural Roads Project - Tranche 1 | 18IN01 | State of Bihar | Transport Infrastructure | CPE | 2024 | The Republic of India | Sovereign | 2018-05-28 | 2018-11-20 | 2019-01-22 | 2023-11-19 | 2023-11-19 | 500 |  | 45 out of USD 350 Million | 45 | 100% | 15 | USD 150 Million | Government of Bihar | Bihar Rural Road Development Agency | 4 | 5 | 4 | 5 | 4 | 5 | 5 | 4
India | Bihar Rural Roads Project - Tranche 2 | 18IN01 | State of Bihar | Transport Infrastructure | CPE | 2024 | The Republic of India | Sovereign | 2022-08-09 | 2022-11-09 | 2022-12-23 | 2025-11-08 | 2025-11-08 | 500 |  | 165 out of USD 350 Million | Ongoing | Ongoing | 6 | USD 150 Million | Government of Bihar | Bihar Rural Road Development Agency | 4 | 5 | 4 | N/A | N/A | 4 | 4 | 4
India | Madhya Pradesh Multi Village Water Supply Project | 17IN02 | Madhya Pradesh State | Water and Sanitation | CPE | 2024 | The Republic of India | Sovereign | 2017-08-30 | 2018-08-20 | 2019-02-21 | 2022-08-19 | 2022-08-19 | 670 |  | 470 | 246.22 | 52% | 51 | USD 200 Million | Government of Madhya Pradesh | Madhya Pradesh Jal Nigam Maryadit | 4 | 4 | 3 | N/A | N/A | 4 | 4 | 4
India | Rajasthan Water Sector Restructuring Project - Tranche 1 | 17IN01 | Rajasthan | Water and Sanitation | CPE | 2024 | The Republic of India | Sovereign | 2017-11-20 | 2018-02-13 | 2018-05-31 | 2023-08-12 | 2023-08-12 | 495 |  | 100 out of USD 345 Million | 100 | 100% | 17 | USD 150 Million | Government of Rajasthan | Government of Rajasthan | 5 | 4 | 4 | 5 | 4 | 5 | 5 | 4
India | Madhya Pradesh Major District Roads II Project | 18IN02 | Madhya Pradesh State | Transport Infrastructure | CPE | 2024 | The Republic of India | Sovereign | 2018-09-18 | 2018-10-05 | 2019-01-17 | 2023-10-04 | 2024-04-04 | 470 |  | 320 | 294.8692 | 92% | 15 | USD 150 Million | Government of Madhya Pradesh | Government of Madhya Pradesh | 5 | 5 | 5 | N/A | N/A | 4 | 5 | 5
India | Madhya Pradesh Bridges Project - Tranche 1 | 18IN03 | Madhya Pradesh State | Transport Infrastructure | CPE | 2024 | The Republic of India | Sovereign | 2018-09-18 | 2018-10-05 | 2019-01-17 | 2023-10-04 | 2023-10-04 | 250 |  | 105 out of USD 175 Million | 105 | 100% | 13 | USD 75 Million | Government of Madhya Pradesh | Government of Madhya Pradesh | 4 | 5 | 5 | 5 | 4 | 5 | 5 | 5
India | Mumbai Metro Rail (Line 2&7) Project | 18IN04 | Maharashtra | Transport Infrastructure | CPE | 2024 | The Republic of India | Sovereign | 2018-11-16 | 2018-12-26 | 2019-05-28 | 2023-12-25 | 2025-06-30 | 2500 |  | 260 | Ongoing | Ongoing | 96 | USD 926 Million USD 1,314 Million | Other Banks Mumbai Metropolitan Region Development Authority | Mumbai Metropolitan Region Development Authority | 6 | 5 | 5 | 5 | N/A | 5 | 5 | 5
India | Assam Bridge Project | 19IN01 | State of Assam | Transport Infrastructure | CPE | 2024 | The Republic of India | Sovereign | 2019-07-08 | 2019-08-08 | 2019-10-23 | 2024-08-07 | 2024-12-31 | 377 |  | 300 | Ongoing | Ongoing | 39 | USD 77 Million | State Government of Assam | Government of Assam | 5 | 5 | 4 | N/A | N/A | 4 | 5 | 5
India | REC Renewable Energy Sector Development Project | 19IN04 | Nationwide | Clean Energy and Energy Efficiency | CPE | 2024 | REC Limited | Non-Sovereign | 2019-10-14 | 2020-05-26 | 2020-05-26 | 2022-06-02 | 2022-06-02 | 426.83 |  | 300 | 300 | 100% | 1 | USD 126.83 Million | Counterpart Funds | REC Limited | 5 | 5 | 4 | 5 | 4 | 5 | 5 | 5
India | Manipur Water Supply Project | 19IN05 | State of Manipur | Water and Sanitation | CPE | 2024 | The Republic of India | Sovereign | 2019-12-02 | 2020-06-03 | 2020-06-12 | 2025-06-02 | 2025-06-02 | 390 |  | 312 | Ongoing | Ongoing | 10 | USD 78 Million | Government of Manipur | Government of Manipur | 5 | 4 | 4 | N/A | N/A | 4 | 5 | 4
India | National Investment and Infrastructure Fund: Fund of Funds − I | 20IN02 | Nationwide | Multiple Areas | CPE | 2024 | National Investment and Infrastructure Fund Limited | Non-Sovereign (Equity) | 2020-03-25 | 2021-02-10 | 2021-02-10 |  |  | INR 42,810 Million |  | 100 |  |  | 23 | USD 480 Million | Other sources | National Investment and Infrastructure Fund Limited | 5 | 5 | 5 | N/A | N/A | 5 | 5 | 5
India | Delhi-Ghaziabad-Meerut Regional Rapid Transit System Project | 20IN04 | National Capital Region; State of Uttar Pradesh | Transport Infrastructure | CPE | 2024 | The Republic of India | Sovereign | 2020-09-29 | 2020-11-19 | 2020-12-22 | 2027-08-31 | 2027-08-31 | 3759 |  | 418 | Ongoing | Ongoing | 91 | USD 1,049 Million USD 500 Million USD 3 Million USD 1,789 Million | Asian Development Bank Asian Infrastructure Investment Bank Japan Fund for Poverty Reduction Government and other sources | National Capital Region Transport Corporation Limited | 6 | 5 | 5 | N/A | N/A | 5 | 5 | 5
Last updated - 20/11/2024

## Evaluation criteria
Evaluation criteria
RATING SCALE
6 - Highly Successful The project achieved or surpassed all main targets, objectives, expectations, and results and can be considered as a model within its project typology (overwhelming positive results and no shortcomings).
5 - Successful The project achieved almost all (indicatively, over 80-95%) of the main targets, objectives, expectations, and results (strong results, with minor shortcomings).
4 - Moderately Successful The project achieved the majority (indicatively, 60 to 80%) of the targets, objectives, expectations, and results. However, a significant part of these was not achieved (positive results with some shortcomings in several areas).
3 - Moderately Unsuccessful The project did not achieve its main targets (indicatively, less than 60%), objectives, expectations, and results (several shortcomings that outweigh some positive results).
2 - Unsuccessful The project achieved only a minority of its targets, objectives, expectations, and results (largely negative results, with very few positive results).
1 - Highly Unsuccessful The project achieved almost none of its targets, objectives, expectations, and results (significant negative results, with hardly any positive results).

## Glossary
Abbreviations
Evaluation Type
PCRV | Project Completion Report Validation
PPE | Project Performance Evaluation
CPE | Country Portfolio Evaluation